## ReadMe & Assumptions
Airbnb Antwerp Pricing Dashboard — Solo Submission Checklist
Individual execution tracker, adapted from the 5-learner team plan. Read this sheet first.
Why this workbook exists | The capstone was scoped as a 5-person team project (see Airbnb_PowerBI_Project_Plan.xlsx). Due to team time-coordination issues, it is being built and submitted individually. This workbook is the actual execution/QA tracker; the original team plan is kept and submitted unmodified as required reference material — do not edit or replace it.
How to use this workbook | 1) Work through 'Task Checklist' top to bottom, phase by phase. 2) Set Status via the dropdown as you go. 3) Log actual hours so you can see effort drift vs estimate. 4) Use 'QA & Validation' before you consider the build done. 5) Use 'Presentation & Docs' and 'Final Submission Pack' in the last few days.
Assumptions (part of the final deliverable) | The numbered assumptions below are also written out in full in Section 0 of Airbnb_Power_BI_Step_by_Step_Guide.md. Copy them (or a summary) into your technical documentation / final slide so a grader sees what was assumed vs. specified.
1. Individual submission | Team plan Excel is submitted as-is as evidence of the original intended plan; solo submission of a team assignment is assumed acceptable. Confirm with instructor if a separate individual-contribution statement is required.
2. Timeline | Confirmed deadline: 20 Sep, extended to 27 Sep (instructor-granted). Personal leave 13 Sep 11:00 IST - 22 Sep with no work possible. Professor agreed a WIP submission on the morning of 13 Sep satisfies the interim checkpoint; final polished version follows 23-26 Sep. See 'Timeline' sheet for the real dated schedule.
3. Scenario baseline | Baseline = 70% occupancy x 1.00x seasonal multiplier. Not specified in the brief; chosen as a neutral midpoint. Change once in the DAX if the instructor specifies otherwise.
4. Pricing field | 'Price' (not 'Adjusted Price') is the primary field for every KPI and scenario measure, since the brief does not distinguish the two.
5. Availability vs. bookings | available = 0 means unavailable/blocked only, never 'booked'. All revenue figures are labeled as scenario projections over loaded, priced calendar rows, not observed bookings.
6. Partial calendar extract | Each listing has only 151-209 of 365 days loaded. The default Projected Revenue KPI covers loaded rows only; any annualized figure is a clearly labeled estimate, never the headline KPI.
7. Null host location | 3 listings have a null Host Location. Left blank rather than backfilled as 'Unknown', to avoid manufacturing a false category. Documented here as a deliberate choice.
8. No RLS / single owner | No row-level security or multi-user access control is built; this is a single-owner academic deliverable, not a production deployment.
9. Publishing | Publishing to Power BI Service assumes a Power BI account/license is available. If the rubric accepts Desktop-only evidence (screenshots), publishing is best-effort rather than a hard blocker.
10. Documentation scope | Deliverables intentionally exceed the brief's minimum ask: a findings presentation deck and a combined user guide/technical document are added, benchmarked against the 'Rainfall vs Agriculture' submission for quality.
Two Excel files — do not merge | Airbnb_PowerBI_Project_Plan.xlsx = original team plan (unmodified, submitted as reference). Airbnb_Solo_Submission_Checklist.xlsx (this file) = actual solo execution/QA tracker.
Instructor guidance folded in | Two course-recording-derived additions now shape this project: (1) a dashboard quality checklist (see 'Dashboard Quality Checklist' sheet) that functions as a de facto grading rubric even though not formally graded; (2) a CIIA (Context-Insight-Implication-Action) + 'three-question rule' narrative framework for the findings deck (see 'Presentation & Docs' sheet and Guide Section 25). Technical correctness alone was explicitly called 'necessary but insufficient' by the instructor.
Presenter's script — why it exists | There is a 9-day gap (13-22 Sep personal leave) between building the dashboard and presenting it. Airbnb_Presentation_Script.md is a near-verbatim speaker script (not just slide bullets) so presentation day is a read/rehearse task, not a from-memory reconstruction. Draft it with placeholders before the 12 Sep build; fill in real numbers 23-25 Sep. See Guide Section 25.4.

## Task Checklist
Task Checklist
Deduplicated from the 5-learner plan into one solo owner. Update Status and Actual Hours as you go.
Phase | Task | Subtasks | Guide Section(s) | Est. Hours (solo) | Actual Hours | Status | Owner | Notes / Decisions Logged
A. Kickoff & Setup | A.1 Dataset connectivity | Identify file formats; configure Power BI data sources; verify refresh settings. | 3 | 10 | 0 | Not Started | You
B. Data Transformation & Cleaning | B.1 Calendar table transformation | Strip currency symbols from price/adjusted_price; convert available to boolean; handle nulls in minimum/maximum nights; enforce date formats. | 4.3 | 10 | 0 | Not Started | You
B. Data Transformation & Cleaning | B.2 Listings, Hosts & Reviews cleaning | Parse amenities into bridge table; trim/standardize property_type & room_type; parse bathrooms_text; clean host_since; clean review dates. | 4.1, 4.2, 4.4, 4.5 | 10 | 0 | Not Started | You
C. Data Modeling & Relationships | C.1 Build star schema & relationships | Identify keys (listing_id, host_id); build DimListing/DimHost/DimDate/FactCalendar/FactReview relationships; enforce single-direction filters except amenity bridge. | 5 | 15 | 0 | Not Started | You
C. Data Modeling & Relationships | C.2 Supporting calculated columns | Host tenure at snapshot; price bin for histogram. | 6 | 8 | 0 | Not Started | You
D. DAX Calculations & Measures | D.1 Core measures | Inventory, price, availability, review measures per Section 8.1-8.2. | 8.1, 8.2 | 15 | 0 | Not Started | You
E. Advanced Analytics & Scenario Modeling | E.1 What-If parameters & scenario DAX | Occupancy Rate & Seasonal Multiplier parameters; Projected Revenue, Baseline Projected Revenue, variance measures, dynamic labels. | 7, 8.3, 8.5 | 20 | 0 | Not Started | You
F. Visualization & UX Design | F.1 Build 3 core report pages | Overview, Listing Analysis, Scenario Insights — KPI cards, map, histogram, tables, charts, slicers, sync slicers. | 10, 11, 12 | 35 | 0 | Not Started | You
F. Visualization & UX Design | F.2 Interactivity, drill-through & tooltip | Listing Detail hidden drill-through page; hidden report-page tooltip; bookmarks (reset + typical/all-price); bookmark navigator. | 13, 14, 15 | 12 | 0 | Not Started | You
G. Testing, QA & Optimization | G.1 Data validation & DAX testing | Reconcile against Section 16 expected-value table; run all 11 behavioral tests; fresh-eyes self-review pass on a different day. | 16 | 10 | 0 | Not Started | You
G. Testing, QA & Optimization | G.2 Performance tuning | Run Performance Analyzer; address slow visuals/DAX; confirm interactions under ~2-3s. | 17 | 5 | 0 | Not Started | You
H. Documentation & Deployment | H.1 User guide & technical documentation | Combined user guide + technical doc: navigation, DAX list, model diagram, validation results, assumptions list. | 20, 25.2 | 12 | 0 | Not Started | You
H. Documentation & Deployment | H.2 Publish & share | Publish to Power BI Service; configure/verify refresh; screenshot evidence if gateway unavailable. | 19 | 5 | 0 | Not Started | You
I. Presentation Deliverable | I.1 Findings presentation deck | 10-slide deck: objective/dataset, model, scenario design, dashboard walkthrough, insights, worked example, recommendations, limitations/conclusion, sources. | 25.1 | 8 | 0 | Not Started | You
J. Wrap-up | J.1 Self check-ins & retrospective | End-of-session check-ins (replaces team stand-ups); short retro notes; final packaging of submission files. | 23 | 3 | 0 | Not Started | You
TOTAL

## Timeline
Solo Timeline (actuals — confirmed 20/27 Sep deadline)
Real dated schedule around confirmed deadline (20 Sep, extended to 27 Sep) and personal leave (13 Sep 11:00 IST - 22 Sep). See Guide Section 24.
Date | Day | Focus | Guide Sections | Exit Criteria / Deliverable | Status
5-6 Sep | Sat-Sun | Kickoff, dataset connectivity, start Calendar cleaning | 3, 4.3 | Sources connected; staging queries created; Calendar price/date cleaning underway. | Not Started
7-8 Sep | Mon-Tue | Finish cleaning (Listings/Hosts/Reviews, amenities bridge); build star schema & relationships | 4.1-4.5, 5, 6 | Star schema built; relationships validated; DimDate marked as date table. | Not Started
9-10 Sep | Wed-Thu | Core DAX measures; What-If parameters & scenario DAX | 8.1-8.2, 7, 8.3-8.5 | QA page shows Total Listings=1,749, Total Hosts=1,111, Calendar Rows=319,192; both What-If parameters work. | Not Started
11 Sep | Fri | Core report pages - Overview and Listing Analysis | 10, 11 | Both pages substantially built with KPI cards, slicers, map, histogram, top-listings table. | Not Started
12 Sep (tonight) | Sat | Scenario Insights page, drill-through/tooltip/bookmarks, QA, performance pass, publish, first documentation draft | 12-19 | All 3 visible pages + hidden pages done; Section 16 checkpoints and behavioral tests run; refresh timestamp visible; pbix published or screenshot evidence captured. | Not Started
13 Sep (before 11:00 IST) | Sun | Final review; package and submit WIP version | - | WIP submitted to professor as the agreed interim checkpoint - not a default, per prior agreement. | Not Started
13 Sep 11:00 - 22 Sep | - | PERSONAL LEAVE - no work planned or possible | - | - | Not Started
23-25 Sep | Wed-Fri | Resume: address professor feedback on WIP; finalize user guide/technical doc; build findings deck and presenter's script | 20, 25 | Documentation complete; findings deck drafted with real KPI values; presenter's script (25.4) finalized. | Not Started
26 Sep | Sat | Final packaging, rehearsal using presenter's script, submit final version | 25.3 | Full submission package complete and submitted - one day inside the 27 Sep extended deadline as buffer. | Not Started

## QA & Validation
QA & Validation Checklist
Reconciliation checkpoints and behavioral tests from Guide Section 16. Do this on a different day than the build.
# | Check | Expected Value / Behavior | Your Result | Pass?
1 | Total Listings | 1,749 |  | Not Tested
2 | Total Hosts | 1,111 |  | Not Tested
3 | Calendar Rows | 319,192 |  | Not Tested
4 | Priced Calendar Nights | 319,117 |  | Not Tested
5 | Available Nights | 170,829 |  | Not Tested
6 | Unavailable or Blocked Nights | 148,363 |  | Not Tested
7 | Availability Rate | 53.5192% |  | Not Tested
8 | Average Price | EUR 109.9178 |  | Not Tested
9 | Review Count (no date filter) | 62,987 |  | Not Tested
10 | Reviewed Listings | 1,525 |  | Not Tested
11 | Baseline Projected Revenue @ 70%/1.00x | EUR 24,553,642.40 |  | Not Tested
12 | Projected Revenue @ 80%/1.10x | EUR 30,867,436.16 |  | Not Tested
13 | Behavioral test: occupancy 70%->80% (multiplier fixed) | Projected Revenue increases by 14.2857% |  | Not Tested
14 | Behavioral test: multiplier 1.00x->1.10x (occupancy fixed) | Scenario Price and Projected Revenue increase by 10% |  | Not Tested
15 | Behavioral test: 70%/1.00x baseline | Projected Revenue = Baseline Projected Revenue; variance = 0 |  | Not Tested
16 | Behavioral test: single Listing ID filter | Manually verify sum(price) x occupancy x multiplier for that listing |  | Not Tested
17 | Behavioral test: date/property/room slicers | Filter every intended visual |  | Not Tested
18 | Behavioral test: Lifetime Review Count with 2022 date filter | Remains available (uses REMOVEFILTERS on DimDate) |  | Not Tested
19 | Behavioral test: map coordinates | Fall around Antwerp; not aggregated |  | Not Tested
20 | Behavioral test: null prices | Do not become zero-price histogram bins |  | Not Tested
21 | Behavioral test: amenity filtering | Works without relationship ambiguity |  | Not Tested
22 | Behavioral test: drill-through | Works from multiple source visuals; Back button works |  | Not Tested
23 | Behavioral test: tooltips | Verified after publishing, not only in Desktop |  | Not Tested

## Presentation & Docs
Presentation & Documentation Checklist
10-slide findings deck + combined user guide/technical doc. See Guide Section 25.
Deliverable | Slide/Section | Content | Status
Findings deck | 1. Title | Project name, your name, Antwerp geography, 26 Dec 2021-25 Dec 2022 window, 1,749 listings. | Not Started
Findings deck | 2. Objective & dataset | Restate Problem Statement objective (the Context for everything after); coverage table from Guide Section 2. | Not Started
Findings deck | 3. Data prep & star schema | Model diagram; top cleaning decisions (null prices never zeroed; available=0 != booked; partial calendar). | Not Started
Findings deck | 4. What-if scenario design | Two parameters; baseline (70%/1.00x) framed as assumption -> purpose -> implication; Projected Revenue formula in plain English. | Not Started
Findings deck | 5. Dashboard walkthrough - Overview | Screenshot + 2-3 line narrative. | Not Started
Findings deck | 6. Dashboard walkthrough - Listing/Scenario | Screenshots + one scenario slider change told as assumptions -> impact -> implication -> risk. | Not Started
Findings deck | 7. Key insights | 5-7 findings, each run through CIIA (Context-Insight-Implication-Action) + 'what changed / why it matters / what to do', grounded in actual computed numbers. | Not Started
Findings deck | 8. Worked example | One listing/room type through occupancy + multiplier change via the assumptions -> impact -> implication -> risk template; state what it does/doesn't imply. | Not Started
Findings deck | 9. Recommendations | 5-7 recommendations written as CIIA Actions: owner + move + timeframe + measure. No vague 'optimize X' phrasing. | Not Started
Findings deck | 10. Limitations, assumptions, conclusion, sources | Pull from Guide Section 0 assumptions + Section 20 limitations; one-sentence conclusion answering 'what should the reader do'; source files. | Not Started
User guide + technical doc | Navigation & scenario controls | From Guide Section 20. | Not Started
User guide + technical doc | Data model diagram | Star schema visual. | Not Started
User guide + technical doc | DAX measure list | Full list with one-line descriptions, from Guide Section 8. | Not Started
User guide + technical doc | What-If parameter setup steps | From Guide Section 7. | Not Started
User guide + technical doc | Validation results | Section 16 table filled in with your actual results. | Not Started
User guide + technical doc | Assumptions list | From Guide Section 0, in full. | Not Started

## Dashboard Quality Checklist
Dashboard Quality Checklist
From the course's recorded expectation-setting sessions - treat as a de facto grading rubric. Apply to every page. See Guide Section 9.1.
Check | Overview page | Listing Analysis page | Scenario Insights page
Chart type matches data shape (trend->line, category->bar, category+subgroup->stacked bar, numeric-vs-numeric->scatter) | Not Checked | Not Checked | Not Checked
Color palette limited to the Section 9 palette - no extra colors added per visual | Not Checked | Not Checked | Not Checked
Good/bad values visually emphasized (Positive/Warning colors used purposefully, not every KPI neutral) | Not Checked | Not Checked | Not Checked
Title states the business purpose, not a generic label (no 'Dashboard' / 'Report' as the whole title) | Not Checked | Not Checked | Not Checked
Large numbers scaled (K/M) via Display Units, not shown as raw multi-digit numbers | Not Checked | Not Checked | Not Checked
No ALL CAPS titles or labels | Not Checked | Not Checked | Not Checked
No metric repeated twice on the same page | Not Checked | Not Checked | Not Checked
Every visual has a visible data label | Not Checked | Not Checked | Not Checked
No raw column/field names leak into a visual title or tooltip | Not Checked | Not Checked | Not Checked
Consistent alignment and clear separation between cards / slicers / chart areas | Not Checked | Not Checked | Not Checked

## Final Submission Pack
Final Submission Pack
Files to submit. See Guide Section 25.3.
File | Purpose | Included?
Airbnb_Antwerp_Pricing_Dashboard.pbix | The built report. | No
Airbnb_Findings_Presentation.pptx | 10-slide findings deck (Section 25.1). | No
Airbnb_User_Guide_and_Technical_Documentation.pdf | Combined user guide + technical doc (Section 25.2). | No
Airbnb_Presentation_Script.md | Presenter's script for the live presentation, bridging the 13-22 Sep leave gap (Section 25.4). | No
Airbnb_PowerBI_Project_Plan.xlsx | Original team plan, submitted unmodified as required reference material. | No
Airbnb_Solo_Submission_Checklist.xlsx | This workbook - actual individual execution/QA tracker. | No
Airbnb_Power_BI_Step_by_Step_Guide.md | Build guide (optional to submit; export to PDF if included). | No